## Sheet1
Requirement specification
|  | Product/Project name: | Project 4 / RAUTE
|  | Author: | Team Network Training
|  | Date updated: | 2021-11-10
[5 empty] | 1 - CRITICAL |  | 1 - DRAFT
[5 empty] | 2 - MAJOR |  | 2 - APPROVED
[5 empty] | 3 - MINOR |  | 3 - REJECTED
4 - POSTPONED
5 - IMPLEMENTED
6 - TESTED
7 - RELEASED
ID | Req. Name | Description | Rationale | Owner | Priority | Date updated | Status | acceptance criteria
Network Training
1.1 | Raw data reading | Raw data must be read using Python | Python is the language of choice, and therefore raw-data json-files must be read using Python libraries. | Team Network Training | 1 - CRITICAL | 2021-12-10 | 7 - RELEASED | When Python is used.
1.2 | Data preprocessing | All sheets must have same number of features in preprocessed data. | Neural network requires that all data rows have same shape. | Team Network Training | 1 - CRITICAL | 2021-12-10 | 7 - RELEASED | Neural network doesn't give errors when input data is fed.
1.3 | Data preprocessing | Preprocessed features must be extracted from these raw data features: - Object data: m_uWidth, m_uLength, m_dThickness, ObjectResX, ObjectResY - All moisture blocks: Moisture, Temperature, m_pntTL, m_pntTR, m_pntBL, m_pntBR - All density blocks: Density, m_pntTL, m_pntTR, m_pntBL, m_pntBR - From defects: All knots, m_mmpntGravity, DEFECT_FEATURE_BOX_WIDTH From dry sheet: - m_dMoisturePercentage | Moisture, density and knots position and width are presumably the most important features when estimating shrinkage. | Team Network Training | 1 - CRITICAL | 2021-12-10 | 7 - RELEASED | All listed features are picked from raw data json-files.
1.4 | Data preprocessing | Preprocessed features must contain also decay from defects. | Decay seems to be quite common defect, so it might be good to check it's effects on shrinkage. | Team Network Training | 2 - MAJOR | 2021-12-10 | 7 - RELEASED | Decay is added to preprocessed features.
1.5 | Data preprocessing | Preprocessed features must contain all defects. | If there is time and neural network starts working with most important defects, it might be useful to test the effects of rarer defects. | Team Network Training | 3 - MINOR | 2021-12-10 | 7 - RELEASED | All defects are added to preprocessed features.
1.6 | Data preprocessing | Target label must be dry sheet percentual width compared to peeling sheet. | Shrinkage of the sheet width is the predicted feature. | Team Network Training | 1 - CRITICAL | 2021-12-10 | 7 - RELEASED | Dry sheet value m_uWidth is used as predicted feature either as it is, or as a percentual difference between peel sheet m_uWidth.
1.7 | Database | Preprocessed data must be stored to database using MariaDB. | Further usage and neural network training is easier when using database. | Team Network Training | 1 - CRITICAL | 2021-12-10 | 7 - RELEASED | MariaDB is up, accessible and contains table with preprocessed data.
1.8 | Database | Database where preprocessed data is stored must accessible by Team 2 and Team 3. | Distributed training and web ui requires access to the preprocessed data. | Team Network Training | 1 - CRITICAL | 2021-12-10 | 5 - IMPLEMENTED | Teams 2 and 3 can access to the database.
1.9 | Database | Information on paired sheets must be saved in its own table in the same database where preprocessed data is stored. | Pairing sheets will be more agile if amount data increases when using database instead of csv-files. | Team Network Training | 2 - MAJOR | 2021-12-10 | 6 - TESTED | MariaDB contains table with information on sheet pairs.
1.10 | Neural network | Neural network must be able to read preprocessed data from the database. | If amount of data is high, it might be necessary to read data directly from database. | Team Network Training | 1 - CRITICAL | 2021-12-10 | 7 - RELEASED | Neural network doesn't give errors when trying to get data from database.
1.11 | Neural network | After reading data from the database, data must be normalized. | Normalizing is usually critical for neural network performance. | Team Network Training | 1 - CRITICAL | 2021-12-10 | 7 - RELEASED | All features are normalized, looks reasonable and doesn't give errors when feeding to neural network.
1.12 | Neural network | Preprocessed data must be divided into training and test sets using to-be-chosen-later distribution. | Splitting data to training and test set is important for confirming accuracy of the neural network. | Team Network Training | 1 - CRITICAL | 2021-12-10 | 7 - RELEASED | Data is split randomly and in decided distribution.
1.13 | Neural network | Hyperparameters and loss function must be chosen in a way, that neural network starts learning the best. | It might require testing to find suitable hyperparameters and loss function, but good choices are crucial for the learnability of the neural network. | Team Network Training | 1 - CRITICAL | 2021-12-10 | 7 - RELEASED | Neural network starts learning with given parameters.
1.14 | Neural network | Trained network must be saved for later training. | With saving the network it is possible to continue training later. | Team Network Training | 1 - CRITICAL | 2021-12-10 | 7 - RELEASED | Saved network is reloadable without errors.
1.15 | Neural network | Neural network must be trainable further with larger dataset. | Inference compatibility is crucial for distributed training. | Team Network Training | 1 - CRITICAL | 2021-12-10 | 7 - RELEASED | Team 2 is able train the network further without errors.
1.16 | Linux shell compatibility | All code must be runnable in Linux shell without graphical user interface. | When using CSC computing power neural networks must be trained using Linux shell. | Team Network Training | 1 - CRITICAL | 2021-12-10 | 4 - POSTPONED | Training is doable in shell without errors.
1.17 | Transferability | Database must be run inside a docker container and have a Dockerfile. | Using docker it is easier to transfer to another environment. | Team Network Training | 1 - CRITICAL | 2021-12-10 | 6 - TESTED | Database runs in docker and is accessible.
1.18 | Pipeline | The whole pipeline must be possible to run using one Python script. | When there is only one script, it is easier to control and to use. | Team Network Training | 1 - CRITICAL | 2021-12-10 | 4 - POSTPONED | Whole pipeline is runnable with one Python script without errors and saved model as end result.
1.19 | Pipeline | It must be possible to provide parameters to pipeline script, in which it is possible to choose which parts of the pipeline will be run: preprocessing and / or training. Also it must be possible to provide through parameters from where the raw data will be read; to where saved model will be stored and how many epoch will be run. | Providing parameters makes it possible to run only desired phases of the pipeline and also to provide new raw data. | Team Network Training | 1 - CRITICAL | 2021-12-10 | 4 - POSTPONED | It is possible to provide parameters to the script and it affects to the functionality of the pipeline in user-desired way.
1.20 | Pipeline | The pipeline script must be possible to start using web UI and it must be possible to provide all possible parameters in the script using web UI. | When whole pipeline is runnable using web UI and most basic information is changeable by user, even non-experienced user can easily start training process with new data. | Team Network Training | 2 - MAJOR | 2021-12-10 | 3 - REJECTED | Whole pipeline is runnable through web UI without errors and with saved model as end result.
1.21 | Pipeline | The pipeline must be possible to interrupt using web UI. | If for any reason user wants to interrupt the pipeline - for example if training seems to take longer than expected -, it is good to be able to do it easily. | Team Network Training | 2 - MAJOR | 2021-12-10 | 3 - REJECTED | User can interrupt the progress of the script and it is possible to add as a functianility to web UI.
1.22 | Pipeline | The pipeline must store logs of the progress and possible errors. | With log-files it is possible to follow or monitor pipeline's progress and functionality. | Team Network Training | 2 - MAJOR | 2021-12-10 | 4 - POSTPONED | Logs are stored, they contain progress and error information and they are readable.
Note on G17: 1 - CRITICAL 2 - MAJOR 3 - MINOR
Note on I17: 1 - DRAFT 2 - APPROVED 3 - REJECTED 4 - POSTPONED 5 - IMPLEMENTED 6 - TESTED 7 - RELEASED